## Instructions
1. Save your Timeline Spreadsheet using your system number as the name followed by the month and year submitted. (ex. 4210001_07_2020)
2. On the LSLR_Timeline tab, select insert, then Header & Footer, Enter your system name and number in the Header area. Save the document and then select the view tab, select the normal view on the left hand side. Select the home tab to continue to enter data.
3. On the spreadsheet, list all service addresses that are required to be replaced. If the water system has complete blocks that will be replaced, you may list block addresses if all addresses are intended to be replaced at the same time.
4. Enter the month and year for replacement of each address or block.
5. Enter the reason for each replacement, key below. Please use drop down box for choices.
6. Enter if the address is a school or Licensed Child Care Facility, this does not include home day cares. Please use the drop down box for choices.
7. Save document and upload to the eAR LSLR tab under document type "Replacement Timeline SS".
LSL - Lead User Service Line - Service line made of lead
LFG - Lead Fitting Gooseneck (A small lead pipe connecting the main to the service line)
LFP - Lead Fitting Pigtail (A small lead pipe connection the service line to the meter)
LF - Lead Fitting - other than a pigtail or gooseneck
USL - Unknown material service line
UF - Unknown material fitting
S - School, K-12 school
LCCC - Licensed Child Care Center - means a child care faclity other than a family day care home
NA - not applicable to this location

## LSLR_timeline
User Service Line location (address or general area): | Date user line to be replaced | Type of user service line (LSL, LFG. LFP. LF, USL, UF): | School or LCCC | Replaced or Identified non-lead | Date completed
1601 Amberwood Drive | 2020-12-01 | LFG | NA
1607 Amberwood Drive | 2020-12-01 | LFG | NA
1627 Amberwood Drive | 2020-12-01 | LFG | NA
1633 Amberwood Drive | 2020-12-01 | LFG | NA
1643 Amberwood Drive | 2020-12-01 | LFG | NA
1645 Amberwood Drive | 2020-12-01 | LFG | NA
1653 Amberwood Drive | 2020-12-01 | LFG | NA
1675 Amberwood Drive | 2020-12-01 | LFG | NA
1681 Amberwood Drive | 2020-12-01 | LFG | NA
1689 Amberwood Drive | 2020-12-01 | LFG | NA
1699 Amberwood Drive | 2020-12-01 | LFG | NA
2012 Amherst Drive | 2020-12-01 | LFG | NA | Replaced | 2019-06-01
521 Arroyo Square | 2020-12-01 | LFG | NA
522 Arroyo Square | 2020-12-01 | LFG | NA
524 Arroyo Square | 2020-12-01 | LFG | NA
525 Arroyo Square | 2020-12-01 | LFG | NA
308 Arroyo Drive | 2020-12-01 | LFG | NA
314 Arroyo Drive | 2020-12-01 | LFG | NA
318 Arroyo Drive | 2020-12-01 | LFG | NA
400 Arroyo Drive | 2020-12-01 | LFG | NA
414 Arroyo Drive | 2021-12-01 | LFG | NA
418 Arroyo Drive | 2021-12-01 | LFG | NA
424 Arroyo Drive | 2021-12-01 | LFG | NA
430 Arroyo Drive | 2021-12-01 | LFG | NA
510 Arroyo Drive | 2021-12-01 | LFG | NA
516 Arroyo Drive | 2021-12-01 | LFG | NA
520 Arroyo Drive | 2021-12-01 | LFG | NA
600 Arroyo Drive | 2021-12-01 | LFG | NA
610 Arroyo Drive | 2021-12-01 | LFG | NA
654 Arroyo Drive | 2021-12-01 | LFG | NA
664 Arroyo Drive | 2021-12-01 | LFG | NA
700 Arroyo Drive | 2021-12-01 | LFG | NA
712 Arroyo Drive | 2021-12-01 | LFG | NA
932 Arroyo Drive | 2021-12-01 | LFG | NA
910 Buena Vista Street | 2021-12-01 | LFG | NA
917 Buena Vista Street | 2021-12-01 | LFG | NA
918 Buena Vista Street | 2021-12-01 | LFG | NA
928 Buena Vista Street | 2021-12-01 | LFG | NA
1000 Buena Vista Street | 2021-12-01 | LFG | NA
1023 Buena Vista Street | 2021-12-01 | LFG | NA
1037 Buena Vista Street | 2021-12-01 | LFG | NA
1133 Buena Vista Street | 2021-12-01 | LFG | NA
1222 Chelten Way | 2021-12-01 | LFG | NA
1225 Chelten Way | 2021-12-01 | LFG | NA
1300 Chelten Way | 2021-12-01 | LFG | NA
2000 Chelten Way | 2021-12-01 | LFG | NA
216 Fairview Ave | 2021-12-01 | LFG | NA
218 Fairview Ave | 2021-12-01 | LFG | NA
300 Fairview Ave | 2021-12-01 | LFG | NA
302 Fairview Ave | 2021-12-01 | LFG | NA
312 Fairview Ave | 2021-12-01 | LFG | NA
316 Fairview Ave | 2021-12-01 | LFG | NA
320 Fairview Ave | 2021-12-01 | LFG | NA
330 Fairview Ave | 2021-12-01 | LFG | NA
402 Fairview Ave | 2021-12-01 | LFG | NA
414 Fairview Ave | 2021-12-01 | LFG | NA
529 Five Oaks Drive | 2021-12-01 | LFG | NA
533 Five Oaks Drive | 2021-12-01 | LFG | NA
537 Five Oaks Drive | 2021-12-01 | LFG | NA
217 Fremont Ave | 2021-12-01 | LFG | NA
225 Fremont Ave | 2021-12-01 | LFG | NA
307 Fremont Ave | 2021-12-01 | LFG | NA
315 Fremont Ave | 2021-12-01 | LFG | NA
325 Fremont Ave | 2021-12-01 | LFG | NA
2051 Fremont Ave | 2021-12-01 | LFG | NA | Replaced | 2019-11-06
411 Fremont Ave | 2021-12-01 | LFG | NA
208 Grand Ave | 2021-12-01 | LFG | NA
220 Grand Ave | 2021-12-01 | LFG | NA
225 Grand Ave | 2021-12-01 | LFG | NA
302 Grand Ave | 2021-12-01 | LFG | NA
308 Grand Ave | 2021-12-01 | LFG | NA
312 Grand Ave | 2022-12-01 | LFG | NA
333 Grand Ave | 2022-12-01 | LFG | NA
1119 Huntington Drive | 2022-12-01 | LFG | NA
1127 Huntington Drive | 2022-12-01 | LFG | NA
1136 Huntington Drive | 2022-12-01 | LFG | NA
1152 Huntington Drive | 2022-12-01 | LFG | NA
1163 Huntington Drive | 2022-12-01 | LFG | NA
1170 Huntington Drive | 2022-12-01 | LFG | NA
1207 Huntington Drive | 2022-12-01 | LFG | NA
1216 Huntington Drive | 2022-12-01 | LFG | NA
1234 Huntington Drive | 2022-12-01 | LFG | NA
1401 Huntington Drive | 2022-12-01 | LFG | NA | Replaced | 2019-03-01
1431 Huntington Drive | 2022-12-01 | LFG | NA
1505 Huntington Drive | 2022-12-01 | LFG | NA
1509 Huntington Drive | 2022-12-01 | LFG | NA
1513 Huntington Drive | 2022-12-01 | LFG | NA
1521 Huntington Drive | 2022-12-01 | LFG | NA
1625 Huntington Drive | 2022-12-01 | LFG | NA
1636 Huntington Drive | 2022-12-01 | LFG | NA
1644 Huntington Drive | 2022-12-01 | LFG | NA
1652 Huntington Drive | 2022-12-01 | LFG | NA
1656 Huntington Drive | 2022-12-01 | LFG | NA
1672 Huntington Drive | 2022-12-01 | LFG | NA
1627 Laurel Street | 2022-12-01 | LFG | NA
1641 Laurel Street | 2022-12-01 | LFG | NA
1703 Laurel Street | 2022-12-01 | LFG | NA
1711 Laurel Street | 2022-12-01 | LFG | NA
1100 Maple Street | 2022-12-01 | LFG | NA
1104 Maple Street | 2022-12-01 | LFG | NA
1112 Maple Street | 2022-12-01 | LFG | NA
920 Meridian Ave | 2022-12-01 | LFG | NA
1011 Meridian Ave | 2022-12-01 | LFG | NA
1015 Meridian Ave | 2022-12-01 | LFG | NA
1020 Meridian Ave | 2022-12-01 | LFG | NA
1023 Meridian Ave | 2022-12-01 | LFG | NA
1109 Meridian Ave | 2022-12-01 | LFG | NA
1121 Meridian Ave | 2022-12-01 | LFG | NA
1125 Meridian Ave | 2022-12-01 | LFG | NA
1309 Meridian Ave | 2022-12-01 | LFG | NA
1316 Meridian Ave | 2022-12-01 | LFG | NA
1325 Meridian Ave | 2022-12-01 | LFG | NA
1401 Meridian Ave | 2022-12-01 | LFG | NA
1415 Meridian Ave | 2022-12-01 | LFG | NA
2016 Meridian Ave | 2022-12-01 | LFG | NA
2036 Meridian Ave | 2022-12-01 | LFG | NA
1212 Milan Ave | 2022-12-01 | LFG | NA
1217 Milan Ave | 2022-12-01 | LFG | NA
1325 Milan Ave | 2022-12-01 | LFG | NA
1331 Milan Ave | 2022-12-01 | LFG | NA
1405 Milan Ave | 2022-12-01 | LFG | NA
1414 Milan Ave | 2022-12-01 | LFG | NA
409 Mission Street | 2022-12-01 | LFG | NA
425 Mission Street | 2023-12-01 | LFG | NA
430 Mission Street | 2023-12-01 | LFG | NA
440 Mission Street | 2023-12-01 | LFG | NA
444 Mission Street | 2023-12-01 | LFG | NA
454 Mission Street | 2023-12-01 | LFG | NA
141 Monterey Road | 2023-12-01 | LFG | NA
202 Monterey Road | 2023-12-01 | LFG | NA
210 Monterey Road | 2023-12-01 | LFG | NA
1621 Oak Street | 2023-12-01 | LFG | NA | Replaced | 2019-04-01
1625 Oak Street | 2023-12-01 | LFG | NA
1635 Oak Street | 2023-12-01 | LFG | NA
1707 Oak Street | 2023-12-01 | LFG | NA
207 Oaklawn Ave | 2023-12-01 | LFG | NA
217 Oaklawn Ave | 2023-12-01 | LFG | NA
227 Oaklawn Ave | 2023-12-01 | LFG | NA
309 Oaklawn Ave | 2023-12-01 | LFG | NA
317 Oaklawn Ave | 2023-12-01 | LFG | NA
401 Oaklawn Ave | 2023-12-01 | LFG | NA
409 Oaklawn Ave | 2023-12-01 | LFG | NA
415 Oaklawn Ave | 2023-12-01 | LFG | NA
425 Oaklawn Ave | 2023-12-01 | LFG | NA
431 Oaklawn Ave | 2023-12-01 | LFG | NA | Replaced | 2019-10-01
501 Oaklawn Ave | 2023-12-01 | LFG | NA
507 Oaklawn Ave | 2023-12-01 | LFG | NA
526 Oaklawn Ave | 2023-12-01 | LFG | NA
534 Oaklawn Ave | 2023-12-01 | LFG | NA
620 Orange Grove Ave | 2023-12-01 | LFG | NA
631 Orange Grove Ave | 2023-12-01 | LFG | NA
634 Orange Grove Ave | 2023-12-01 | LFG | NA
639 Orange Grove Ave | 2023-12-01 | LFG | NA
648 Orange Grove Ave | 2023-12-01 | LFG | NA
653 Orange Grove Ave | 2023-12-01 | LFG | NA
712 Orange Grove Ave | 2023-12-01 | LFG | NA
800 Orange Grove Ave | 2023-12-01 | LFG | NA
810 Orange Grove Ave | 2023-12-01 | LFG | NA
812 Orange Grove Ave | 2023-12-01 | LFG | NA
332 Pasadena Ave | 2023-12-01 | LFG | NA
334 Pasadena Ave | 2023-12-01 | LFG | NA
361 Pasadena Ave | 2023-12-01 | LFG | NA
390 Pasadena Ave | 2023-12-01 | LFG | NA
396 Pasadena Ave | 2023-12-01 | LFG | NA
400 Prospect Circle | 2023-12-01 | LFG | NA
401 Prospect Circle | 2023-12-01 | LFG | NA
410 Prospect Circle | 2023-12-01 | LFG | NA
411 Prospect Circle | 2023-12-01 | LFG | NA
420 Prospect Circle | 2023-12-01 | LFG | NA
425 Prospect Circle | 2023-12-01 | LFG | NA
430 Prospect Circle | 2023-12-01 | LFG | NA
431 Prospect Circle | 2023-12-01 | LFG | NA
461 Prospect Circle | 2023-12-01 | LFG | NA
471 Prospect Circle | 2023-12-01 | LFG | NA
481 Prospect Circle | 2023-12-01 | LFG | NA
495 Prospect Ave | 2023-12-01 | LFG | NA
501 Prospect Ave | 2023-12-01 | LFG | NA
505 Prospect Ave | 2023-12-01 | LFG | NA
511 Prospect Ave | 2023-12-01 | LFG | NA
519 Prospect Ave | 2023-12-01 | LFG | NA
523 Prospect Ave | 2023-12-01 | LFG | NA
529 Prospect Ave | 2023-12-01 | LFG | NA
533 Prospect Ave | 2023-12-01 | LFG | NA
534 Prospect Ave | 2023-12-01 | LFG | NA
541 Prospect Ave | 2023-12-01 | LFG | NA
1611 Spruce Street | 2023-12-01 | LFG | NA
1637 Spruce Street | 2023-12-01 | LFG | NA
804 Valley View Road | 2023-12-01 | LFG | NA
816 Valley View Road | 2023-12-01 | LFG | NA
830 Valley View Road | 2023-12-01 | LFG | NA
900 Valley View Road | 2023-12-01 | LFG | NA